## Ark1
Areas | Tasks | People |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
|  |  | MA | TUE | WED | THU | FRI | SAT | SUN | MA | TUE | WED | THU | FRI | SAT | SUN | MA | TUE | WED | THU | FRI | SAT | SUN | MA | TUE | WED | THU | FRI | SAT | SUN | MA | TUE | WED | THU | FRI | SAT | SUN
HTML and CSS
| Setting up page structure and create layout | P1 | bar: MA to WEEK 3 SUN
| Setting up page structure and create layout | P2 | bar: MA to WEEK 1 SUN
| Develop orderform | P2 | bar: WEEK 1 MA to WEEK 2 SUN
| Develop costumerservice | P2 | bar: WEEK 2 MA to WEEK 3 SUN
| Make a clean and obvious navigation structure | P1 | bar: WEEK 3 MA to WEEK 4 SUN
Design
| Take pictures | P3 | bar: MA to WEEK 1 SUN
| Create colorpallet | P3 | bar: MA to WEEK 1 SUN
| Create neat and complete product information | P3 | bar: WEEK 1 MA to WEEK 3 SUN
| Adding details | P3 | bar: WEEK 3 MA to WEEK 4 SUN
Marketing
| Write texts for Website | P4 | bar: WEEK 1 MA to WEEK 2 SUN
| Creating Articles | P4 | bar: WEEK 2 MA to WEEK 3 SUN
| Planning launch | P4 | bar: WEEK 3 MA to WEEK 4 SUN
| Responsible for copywright and content | P4 | bar: MA to WEEK 4 SUN
Finishing and launching
| Fixing bugs, adding details and finishing up | Everybody | bar: WEEK 4 MA to WEEK 5 SUN
Meeting
| Meeting with costumer | Everybody | bar: MA; WEEK 1 MA; WEEK 2 MA; WEEK 3 MA; WEEK 4 MA; WEEK 5 SUN
| Meeting with team | Everybody | bar: TUE; WEEK 1 SUN; WEEK 1 TUE; WEEK 2 SUN; WEEK 2 TUE; WEEK 3 SUN; WEEK 3 TUE; WEEK 4 SUN; WEEK 4 TUE; WEEK 5 SAT
P1 | HTML and CSS specialist
P2 | HTML and CSS specialist
P3 | Design and photographer
P4 | Expert in marketing